## Sheet1
Comments | Responses | Draft response to users
1. Benchmarking doesn’t seem to work, as it seems to refer to Spanish dataset, even though they specify Polish data | Benchmarking: Modifications: First, the dashboard asks users whether they want to include benchmarking. If they say no, benchmarking will not be conducted. If they say yes and the benchmarking target dataset is uploaded, use it to conduct benchmarking. If they say yes but the target dataset is not provided, the benchmarked datasets will be produced using the household survey data with the level of benchmark selected in the dashboard. If no population file is uploaded, estimate domain populations from the survey as sum(weight * household size). If neither is possible, stop/warn clearly instead of using old sample data. | Thank you for flagging this. The benchmarking workflow should be controlled explicitly by the dashboard. If benchmarking is not selected, the app should not run benchmarking or produce benchmarked outputs. If benchmarking is selected and a benchmark target file is uploaded, the app should use that file. If benchmarking is selected but no target file is provided, the app can derive benchmark totals from the household survey at the selected benchmark level, using population weights equal to survey weight times household size. The app should also stop with a clear warning if the required inputs are not available, rather than relying on sample or old data.
2. Shapefiles: The App still seems to draw on Spanish shapefiles even though they upload Polish geometries. The app draws empty Spanish basemaps without estimates | Shapefiles: confirmed. The Comparison stage ignores the uploaded geometry and reads data/geometries.rds directly, assumes prov, and converts IDs to integer. That explains default/Spanish-looking empty maps. See [scripts/03_comparison.R (line 142)](C:/Users/noboy/OneDrive/EU_SAE_application_package/scripts/03_comparison.R:142). | Confirmed. The Comparison stage was still reading the default geometry file rather than consistently using the uploaded geometries, which can lead to Spanish-looking empty maps. The fix is to make the Comparison stage use the geometry file selected in the app configuration, respect the configured geometry ID field, and preserve domain IDs as character values so joins work correctly.
3. The App seems to require a NUTS2 ID to be present in the data even if one does not request the App to do NUTS 2 benchmarking. | NUTS2/region required: currently yes in practice. The code calls it region; because benchmarking is on by default, UFH unconditionally builds region_map <- survey_all ¦> select(domain, region). This should only be required when benchmarking is enabled. | This is a valid issue. The app currently requires the regional/NUTS2-style variable in practice because benchmarking logic is triggered by default and the code builds a region-to-domain map unconditionally. The variable should only be required when the user selects regional/NUTS2 benchmarking. If that benchmarking level is not selected, the app should allow the run to proceed without a NUTS2 field.
4. They were wondering if the output folders/files can have some sort of “label” attached to them to distinguish outputs across runs? The fact that all output files get re-written by default every time you run the App they find to be not very convenient | Run labels/output folders: currently outputs are fixed under outputs/ and overwritten. Please save output folders whenever you complete an analysis. | Agreed. At present, outputs are written to fixed output locations and can be overwritten by later runs. A better workflow is to save each run in its own timestamped and/or user-labeled output folder, and optionally include the run label in exported filenames so results from different runs are easier to distinguish.
5. If one makes a typo, say by specifying year 2018, when the data is for 2019 and 2020, the App will not produce an output, but there also won’t be an informative error that would point the user to the source of the problem. Right now the there is a generic error, something like “wrong list” which makes it hard to spot the typo. | Wrong analysis year typo: confirmed gap. The app checks “exactly two years” and whether survey/auxiliary contain the same year column, but it does not block requested years that are absent from the data. That should become a clear readiness error. | Agreed. The readiness checks should catch this before model execution. The app currently checks basic year structure, but it should also verify that the requested analysis years are actually present in the survey and auxiliary data. If a requested year is missing, the app should stop with a clear message showing the requested years and the years found in the data.
6. Once you upload a benchmarking file, it seems to be impossible to remove it, if you wanted, for instance, to run the App with benchmarking, and then run it again without benchmarking. Now one needs to close the app and re-open it in order to do so. | This issue can be solved by adding the option of benchmarking in the dashboard. | Agreed. The dashboard should include an explicit benchmarking on/off control. When benchmarking is turned off, the app should ignore any previously uploaded benchmarking file for the next run, so users do not need to close and reopen the app to run without benchmarking.
7. In Poland they have 5 years of data 2019-2023, and thy run the App for pairs of years (2019-2020; 2020-2021; 2021-2022; 2022-2023), and for some years they use there is no error, but also no output, just an empty file | Clarification is needed. | Clarification needed from users. Please provide the specific year pairs that produce no output or empty files, the model options selected, the run log, the saved app_config.yml for those runs, and the names of the empty output files. It would also help to know whether the issue occurs in UFH, MFH, Comparison, or final report generation.
8. For some years with smooth_all option the CV estimates become very large for MFH, but not UFH for reasons that are unclear to them. | Identification of sources of high CVs. pov_mfh.xlsx and pov_fh.xlsx include all the information to examine why CV is so high (too high RMSE or too low point estimate). Both are vailable in output/data folder. | The output files pov_mfh.xlsx and pov_fh.xlsx contain the components needed to diagnose this. Since CV is driven by the ratio of RMSE to the point estimate, very large CVs can result from either unusually high RMSEs or very small point estimates. We should compare the affected MFH domains and years against UFH to identify whether the smooth_all option is increasing the RMSE, lowering the point estimate, or both.
9. Some labels don’t seem to update. When they load Polish data for 2019-2020, some results still refer to years 2012-2013 which come from Spanish testing | 2012/2013 labels: confirmed. Several Comparison calls and titles are hard-coded to 2012/2013. See [scripts/03_comparison.R (line 859)](C:/Users/noboy/OneDrive/EU_SAE_application_package/scripts/03_comparison.R:859) and [scripts/03_comparison.R (line 1106)](C:/Users/noboy/OneDrive/EU_SAE_application_package/scripts/03_comparison.R:1106). | Confirmed. Some labels in the Comparison stage are hard-coded to the Spanish test years 2012 and 2013. These should be replaced with the years selected in the app configuration so report titles, plot labels, and exported text update correctly for Polish runs such as 2019-2020.
10. They are wondering it if may be possible for the province variable to be input in string format, as it has leading zeroes in Poland, or does it have to be converted to integer? | Province/domain as string with leading zeroes: not safe today. MFH/Comparison repeatedly coerce domain to integer, which will drop leading zeroes. This should be changed to character IDs throughout joins, maps, benchmark, and exports. | The province/domain variable should be allowed to remain in string format, especially when IDs contain leading zeroes. The current code is not fully safe because some steps coerce IDs to integer, which drops leading zeroes. The fix is to keep domain/province IDs as character values consistently across joins, mapping, benchmarking, and exports.
11. If the welfare variable is input with a typo, say `income2’, the App just crashes and closes mid-execution. Check readiness function in the App does not spot such typos. This only happens with typos in the welfare variable. If you make a typo in the year variable, the App produces an error, as expected. But again, this should be something that is spotted in the “check readiness” step. | Welfare typo crashes: Typos should be spotted in the data readiness stage. If there are errors, the errors should be mentioned and prevent users from moving to the analysis stage. | Agreed. This should be caught during the data readiness step. The app should check that the mapped welfare variable exists in the uploaded survey data before execution begins. If the variable is missing, the readiness assessment should show a clear error and prevent the user from starting the analysis, rather than crashing mid-run.
12. If you choose MFH2, you still get results in the output for MFH1 and MFH2, even though you haven’t asked for MFH1 | Selecting MFH2 still outputs MFH1: Modify the code so that the results of only selected one (MFH1, MFH2, or MFH3) will be presented. | Agreed. If the user selects only MFH2, the app should present only MFH2 results. The output and report logic should be updated so that only the selected MFH method, whether MFH1, MFH2, or MFH3, is included in the final outputs.
13. App produces benchmarking results even if you don’t ask for benchmarking and do not supply a benchmarking file. It is unclear where these come from, as point estimates remain unchanged but MSE numbers are different | Benchmark outputs without asking: same root cause as #1. Internal benchmark targets are computed from direct estimates when no external benchmark file is given. Point estimates may barely change, while MSE changes because benchmarked MSE is recomputed. | This has the same root cause as comment 1. The app currently creates internal benchmark targets from the direct estimates when no external benchmark file is provided, so benchmarked outputs can appear even when the user did not intentionally request benchmarking. Point estimates may remain nearly unchanged, while MSE values can differ because benchmarked MSEs are recomputed. Benchmarking should only run when explicitly selected, and outputs should clearly indicate the benchmark source.
14. When computing sampling variances, it is possible to use the strata ID information in survey design parameters? | Strata in sampling variances: not currently supported. Both UFH and MFH use svydesign(ids = ~psu, weights = ~weight, ...) with no strata. Let's add a strata variable mapping and svydesign(..., strata = ~strata, nest = TRUE). | Strata are not currently used in the sampling variance design. The current setup uses survey design parameters with PSU and weights only. We should add an optional strata variable mapping and, when supplied, pass it to the survey design as strata with nest = TRUE. If no strata variable is supplied, the app can continue using the current no-strata design.
15. There is no selection of the level of benchmarking in the dashboard. For example, users should be able to choose the level of benchmarking as national or region. | Include a quesiton on the level of benchmarking in the dashboard. This should be allowed even if users do not provide the benchmarking target database. The app will produce poverty estimates at the level selected for benchmarking using the household survey data. | Agreed. The dashboard should include a question for the desired benchmarking level, such as national or regional benchmarking. This selection should be available even when no external benchmarking target file is uploaded. In that case, the app should estimate benchmark-level poverty rates from the household survey using population weights and then apply benchmarking at the selected level.